Preliminary Field Check Recommendations

It is recommended this Field Check be scheduled and held in two steps.  Step 1 will be conducted with the utilities to focus on their locations and concerns.  Step 2 will provide review of environmental requirements, right of way issues, drainage and any MOT concerns.

In Step 1, the Project Manager will contact the Area Engineer and Designer (three weeks prior) to schedule time and place for the Field Check.

At the same time the Project Manager will contact each utility and send Field Check Plans with the Utility Check List to be completed for the meeting.

Step 1, Field Check

Offices involved:

•	Project Management

•	Construction

•	Design

•	Utilities

Items to review:

•	How many utilities are involved with the project?

•	Check for utilities not identified on the plans.

•	Are utilities knowledgeable about the road design?

•	Preliminary R/W layout.

•	Sufficient R/W for utilities?

•	If project is “limited access R/W”, will utilities stay in R/W?

•	Is R/W conducive to utility relocation?

•	Will SUE be utilized?

•	What will be the clearing requirements for the project and/or utility relocation?

Preliminary Field Check Recommendations cont’d

For Step 2, the Project Manager will contact (three weeks prior) the following offices to schedule the Preliminary Field Check:

Offices involved:

•	Project Management	•	Environmental

•	Construction	•	Geotechnical

•	Design	•	Real Estate

•	Traffic - District	•	Maintenance

Items to review:

•	What is the life expectancy of the project?

•	Check on the budget.  Is all of the work necessary to complete the intended purpose?

•	What is the construction schedule?

•	Is it an early-season project or mid-season project?

•	Is R/W outside the clear zone?

•	What are the expected permits required and their impact to the schedule?

•	What are the expected environmental restrictions and their impact to the schedule?

•	Conceptual Traffic Maintenance Plan and phasing?  Any detour should be driven.

•	Compare costs/feasibility of staged construction and detour.

•	Check for drives not identified on plans.

•	Intersection layout?

•	Conceptual storm sewer layout.

•	Drainage outlets meet phasing shown?

•	Property relocations?

•	Check for new developments and conditions not noted on the plans.

•	Verify that the construction limits are reasonable. (allows enough work space)

•	Landscaping and erosion control items reasonable?

•	Safety concerns addressed?

•	Maintenance concerns addressed?

•	Any other special concerns, material, local festivals, etc.?

•	Review Commitment Report.

Commonly Missed Items to Check

•	Keep any existing Highway Lighting operating as long as practical during utility relocation and construction.  May be practical to use temporary electrical service.

•	Access/maintenance of existing drives for residents and businesses should be discussed.

•	The final grades and widths of the proposed drives for residents and businesses should be discussed.  The designer should try to make the existing drives either at the existing grades or less.  This may show a cause for additional temporary right of way.

•	Are there any existing survey monuments – such as Section Corners – that need to be maintained?

•	Are there any existing castings such as survey monuments, manholes, inlets, valves, etc – that need to be adjusted to grade?

Other Considerations

•	Construction phasing should be checked to make sure that phase lines are consistent.  Do proposed MOT schemes fit on the bridge decks and do the bridge construction joints work with the adjacent roadway and exiting structures.