## Slide 1: Project Lifecycle Insights From a District Project Manager
Jennifer Beck, PMP Taylor Darrah
Senior Project Manager Project Manager
Greenfield District

## Slide 2: Agenda
Introduction
INDOT Asset Management Cycle
INDOT Project Lifecycle
  Initiation
  Development
  Construction
  Final Closeout
Parting Words
Questions

## Slide 3: Introduction
Greenfield District PM Teams
Tipton/Albany Sub
  Jennifer Beck, Taylor Darrah, Sacha Teague, Kim Szewczak
Greenfield/Cambridge City Sub
  Nathan Riggs, Don McGhghy, Ashleigh Pattison, Jodi Riall
Indy Sub
  Christine Williams, HT Pham, Sarah Doyle, Stacey Sorrell

## Slide 4: Introduction

## Slide 5: Introduction
Taylor Darrah Kim Szewczak Sacha Teague
Jay, Randolph, Delaware Hamilton & Madison Tipton, Howard

## Slide 6: INDOT Asset Management Cycle
Technical Services
Capital Programs
Construction
Maintenance

## Slide 7: INDOT Project Lifecycle
Initiation
Scoping
Development
Progress Reporting
Construction
Oversight
Final Closeout
Team Creation
Programming
Close PO’s
Progress Meetings
Final Review of Contracts
Managing scope, schedule and budget

## Slide 8: INDOT Project Lifecycle - Initiation
New Project Assignment is Made
  Technical Services Scoping
    Virtual Van Trips / Call for Projects
    Mini Scope / Engineering Assessment
  Local Program Funding Award
    Rural or MPO Project Application
    Early Coordination Meeting
Technical Services
Capital Programs
Construction
Maintenance

## Slide 9: INDOT Project Lifecycle - Initiation
New Project Assignment Checklist* for an INDOT Project Manager
  Confirm all scoping documents have been received
  Review for potential project bundling
  Determine appropriate delivery method (in-house, small purchase, on-call, RFP)
  Confirm/Request funding to be programmed and added to the TIP and/or STIP
  Update SPMS
    Project Team
    Schedule
    Risk Assessment
    Log Notes
*Not all inclusive

## Slide 10: INDOT Project Lifecycle - Initiation
Project Scoping Meeting
  Includes Contracts Department
  Discuss appropriate tasks, level of effort, payment schedule, etc.
Project Kickoff Meeting
  Includes Project Team Stakeholders
  Set Expectations
    Preferred communication, Risk Evaluation, Problem Resolution Plan, Decision Making Authority, etc.
  Set Schedule
    INDOT Required Milestones to be programmed into SPMS within 60 days of Project Assignment

## Slide 11: INDOT Project Lifecycle - Initiation
Early Coordination Meeting
  For local projects only
  Rural or MPO funding
  Sets expectations between INDOT PM and the ERC assigned
  Set general schedule

## Slide 12: INDOT Project Lifecycle - Initiation
Interlocal Agreements
  Local Projects
    Boilerplate agreement, per phase
  State/Local Partnerships
    Serves as the Project Charter
    Terms can vary widely project to project
    Outlines roles and responsibilities between agencies
  Project Manager must be intimately familiar with the details

## Slide 13: INDOT Project Lifecycle - Initiation
Project Manager Insights
  Jennifer
    The time spent in the initiation phase can make or break a project. Don’t rush into a kickoff meeting if you’re not ready to get into the weeds.
  Taylor
    Schedules should be customized for each project based on specific needs. No one is entitled to the dates provided in the letting prep schedule, if a Project Manager wants to build in float and have earlier deadlines, they are entitled to request this.
  Sacha
    Project Mangers need to know all members of their project team with roles and responsibilities clearly defined. This includes respective INDOT oversight team members where applicable.
  Kim
    Identifying risks and establishing risk mitigation plans from day one is critical.

## Slide 14: INDOT Project Lifecycle - Development
Carry the project through the Project Development Process
Keep all stakeholders informed and involved…
Technical Services
Capital Programs
Construction
Maintenance

## Slide 15: INDOT Project Lifecycle - Development
District*
  Utilities
  Environmental
  R/W
  Program Director
  ERMS Coordinator
  Local Programs
  Asset Owners
  Scoping
  Construction
  Maintenance
  R/W Permits
  Survey
  *Not all inclusive
Central Office*
  Legal
  Contracts
  Communications
  Legislative Affairs
  Executive Office
  Finance
  Pavement Design
  Hydraulics
  Real Estate
  Waterway Permitting
  Design Review
  Geotech

## Slide 16: INDOT Project Lifecycle - Development
External Stakeholders
  Other State Agencies
    IDEM, DNR, ISP, IEDC, etc.
  Local agencies
    Elected officials, city/county staff
  MPOs
  Local Emergency Responders
    Police, fire, nearby hospitals
  Local Schools Districts
  Local Businesses & Business Organizations

## Slide 17: INDOT Project Lifecycle - Development
Monitor Project Progress
  Progress reports / meetings
Maintain SPMS Data
  Keep the schedule up-to-date
  Update funding program and estimates
    Request TIP/STIP updates as needed
  Update Risk Register monthly
  Add log notes as needed to reflect status updates, issues with resolutions and meetings
  Upload relevant documents/e-mails
Request Change Management when necessary
  Cost increase
  Scope change
  Schedule delay (moving out of current fiscal year)

## Slide 18: INDOT Project Lifecycle - Development
Change Management Expectations
  Scoping Documents
  New Score completed by District Asset Engineer
  Cause/Justification – must be well written, balancing detail with brevity
  Safety Concerns and/or Conditions
  If changing project limits – include PK’s, pavement logs, condition of pavement (slicer data), define how it contributes to overall purpose and need
  Condition of asset (bridge and pavement data) and if it can support a fiscal year change
  New Estimate – what changed, comparison spreadsheet with % increase/decrease
  Have other options been considered?
  Has Value Engineering been applied?
  Change Managements related to scope should be submitted no later than Stage 2
  Change Managements related to cost should be submitted no later than Stage 3

## Slide 19: INDOT Project Lifecycle - Development
Constructability Reviews
  Requested for all stage submittals
  Requires manual upload of stage submittal documents
  Critical for ensuring construction feedback throughout the development process
Document transfers / access to large documents
  ERMS is great for viewing, but not sharing
  Coordinate mutually agreed upon location for sharing project documents
  Independent sharefile sites can be beneficial
Final Tracings Reviews
Annual Fiscal Year Lockdown reviews

## Slide 20: INDOT Project Lifecycle - Development
Review and Approve Consultant Invoices
  Ensure correct PO is being invoiced
  Ensure tasks billing towards line up with progress report/activities witnessed
  Look for typos or errors that could trigger audit issues
Evaluate Consultant Supplemental Fee Requests
Complete Consultant Performance Evaluations
  Stage 1
  Stage 2
  Stage 3
  Final Tracings

## Slide 21: INDOT Project Lifecycle - Development
Local Projects
  Review Quarterly Reports and Attend Quarterly Meetings
    Update Schedules
    Provide feedback on development progress for program administrators
  Assist ERC’s Upon Request
  Project Consultant Reviews at Final Tracings

## Slide 22: INDOT Project Lifecycle - Development
Project Manager Insights
  Jennifer
    It’s unacceptable for a designer to bring a problem to our attention with no solutions or suggested next steps. This is what we are paying for.
  Taylor
    PM – Consultant communication is so important because of the extensive internal communication that is constantly happening. When things change, be it scope, schedule or budget, we need to know why!
  Sacha
    Consultant PMs need to be the ones to keep INDOT PMs informed, you don’t want the INDOT PM to find out about a project problem from someone else. Ensure PMs are included in or aware of all INDOT coordination.
  Kim
    Early communication of potential change managements is tremendously helpful due to the amount of work needed to get them through the process.

## Slide 23: INDOT Project Lifecycle - Construction
Attend Progress Meetings
Ensure project purpose is carried on through construction
Oversee fulfillment of project commitments
Assist with determining participating vs. non-participating change orders
Track Error & Omission change orders
  Recoverable vs. Non-Recoverable
Document and share lessons learned
Oversee the unofficial detour process
When applicable, manage public outreach

## Slide 24: INDOT Project Lifecycle - Construction
Time to build the project!
Project Lead transfers from Project Manager to Project Engineer/Supervisor
Point of transfer occurs at the Pre-Construction Conference
Project Managers are still involved throughout construction
Technical Services
Capital Programs
Construction
Maintenance

## Slide 25: INDOT Project Lifecycle - Construction
Project Manager Insights
  Jennifer
    Designers and Project Managers need to agree with the level of involvement in progress meetings.
  Taylor
    Change Orders – we are required to ensure that the change order is still in compliance with the project planning/environmental/permit documents. Especially when plan revisions are involved.
    Customer Services inquiries are heavier during this phase, so we still need consultant support to address the questions as they arise.
  Sacha
    Lessons learned are so important to improve the quality of future projects. Whenever any are identified throughout the construction process, please ensure the PMs are in the loop.
  Kim
    Include PMs on all correspondence with construction, we’re still involved! And we’re the one’s approving the invoices!

## Slide 26: INDOT Project Lifecycle – Final Closeout
Project Managers ensure timely closeout of all INDOT projects
Make sure final invoices for all phases have been received and paid.
  Ensure contract tasks were fulfilled
    Consultant Contracts
    INDOT/LPA Contracts
    Interlocal Agreements
    Maintenance Agreements

## Slide 27: INDOT Project Lifecycle – Final Closeout
Project Manager Insights
  Jennifer
    Project close out can get really complicated if an error in invoicing is found in audit, PLEASE review invoices before your finance department sends them out to help us avoid a big mess at the end of a project!!
  Taylor
    If a project has been completed for a while and are we asking the consultant if they are done invoicing, there needs to be a very good reason if the answer to that question is no.
  Sacha
    Invoice regularly so that PO’s stay active. At least every 6 months – or explain why you can’t invoice for 6 months. Keep us informed!
  Kim
    Mark your last invoice appropriately so POs don’t sit open indefinitely, even if the balance is zero.

## Slide 28: Parting Words

## Slide 29: Questions?
Jennifer Beck, PMP
Senior Project Manager
Indiana Department of Transportation
Greenfield District
Cell: (765) 745-8276
Email: jbeck@indot.in.gov
Taylor Darrah Project Manager
Indiana Department of Transportation
Greenfield District
Office: (317) 467-3915
Cell: (317) 526-6080
Email: TDarrah@indot.in.gov